## Slide 1
Monthly Project Health Review
July 2026
Professional Services — Executive Summary
Portfolio: 2 Active Projects
0 Green
0 Amber
2 Red
Confidential — For Internal Use Only

## Slide 2
Portfolio Overview
Health status across all active projects
Project | PM | Stage | % Done | Score | RAG | Confidence
Zycus - UniSan S2P Implementation | Rajat Bothra | Training Phase I | 44% | 1.2 | Red | High
Zycus - Titan S2P Implementation | Aftab Hashambhai | Configuration and Bu | 71% | 1.65 | Red | High

## Slide 3
Health Dimensions — Cross-Project View
How each health dimension performs across the portfolio
Schedule Adherence
Amber
Red
Completion Progress
Red
Green
Milestone Health
Amber
Amber
Task Risk Profile
Red
Amber
Stakeholder Signals
Red
Amber
Zycus - UniSan S2P Implem
Zycus - Titan S2P Impleme
⚠ Most common concern: Schedule Adherence (flagged in 2 projects)

## Slide 4
Risk Spotlight
Top risks requiring leadership attention
Zycus - UniSan S2P Implem
🟡 Schedule Adherence: Schedule is under pressure. Average delay is 2.0 days with 100% of baselined tasks running late. M
Zycus - UniSan S2P Implem
🔴 Completion Progress: Project is significantly behind schedule. At only 44% complete vs 59% expected — a 15pp gap. 192
Zycus - UniSan S2P Implem
🟡 Milestone Health: Some milestones need attention. 85% are on track, but 1 are at risk (eProc and eInvoice and Merlin A
Zycus - UniSan S2P Implem
🔴 Task Risk Profile: Task risk profile is concerning. Only 78% of active tasks are Green while 18% are Red. Immediate at
Zycus - UniSan S2P Implem
🔴 Stakeholder Signals: Stakeholder signals are negative: summary health is Red.
Zycus - Titan S2P Impleme
🔴 Schedule Adherence: Schedule is significantly slipping. Average delay is 19.6 days with 64% of tasks running behind ba

## Slide 5
Deep Dive: Zycus - UniSan S2P Implementation
PM: Rajat Bothra
Stage: Training Phase I
Timeline: 2026-02-11 → 2026-10-09
Completion: 0.44
Composite Score: 1.2/3.00
Dimension Scores
Schedule Adherence: Amber
Completion Progress: Red
Milestone Health: Amber
Task Risk Profile: Red
Stakeholder Signals: Red
Key Risks
• 🟡 Schedule Adherence: Schedule is under pressure. Average delay is 2.0 days with 100% of baselined t
• 🔴 Completion Progress: Project is significantly behind schedule. At only 44% complete vs 59% expecte
• 🟡 Milestone Health: Some milestones need attention. 85% are on track, but 1 are at risk (eProc and e
• 🔴 Task Risk Profile: Task risk profile is concerning. Only 78% of active tasks are Green while 18% a
Recommended Actions
1. Review resource allocation — consider adding capacity to critical path tasks.
2. Perform a task-level triage to re-prioritize and resolve blocked items.
3. Schedule a stakeholder alignment meeting to address concerns and reset expectations.

## Slide 6
Deep Dive: Zycus - Titan S2P Implementation
PM: Aftab Hashambhai
Stage: Configuration and Build phase
Timeline: 2025-12-05 → 2026-12-07
Completion: 0.71
Composite Score: 1.65/3.00
Dimension Scores
Schedule Adherence: Red
Completion Progress: Green
Milestone Health: Amber
Task Risk Profile: Amber
Stakeholder Signals: Amber
Key Risks
• 🔴 Schedule Adherence: Schedule is significantly slipping. Average delay is 19.6 days with 64% of tas
• 🟡 Milestone Health: Some milestones need attention. 67% are on track, but 1 are at risk (Phase 1- S2
• 🟡 Task Risk Profile: Task risk profile shows moderate concern. 89% of tasks are Green, but 10% are R
• 🟡 Stakeholder Signals: Mixed stakeholder signals: 3 task(s) on hold; project flagged as High risk; 1
Recommended Actions
1. Conduct an urgent schedule recovery workshop with the PM to identify acceleration opportunities.
2. Perform a task-level triage to re-prioritize and resolve blocked items.
3. Schedule a stakeholder alignment meeting to address concerns and reset expectations.

## Slide 7
Recommendations & Next Steps
1.
Review resource allocation — consider adding capacity to critical path tasks.
2.
Perform a task-level triage to re-prioritize and resolve blocked items.
3.
Schedule a stakeholder alignment meeting to address concerns and reset expectations.
4.
Conduct an urgent schedule recovery workshop with the PM to identify acceleration opportunities.
Next Review
Weekly health reports will continue. Next monthly review scheduled in 4 weeks. Please raise any concerns to the PM or steering committee immediately.